## Sheet1
Issue ID | Login as | Module | Issue Title | Issue Desciption | Assigned Work | Status (Done By) | Issue Date | Expected Result | Actual Result | Result Yes/No | Tester Comments | Reported By | Priority | Classification
ATAUTFRS22001 | Author | section assignment | Merge cells | Merge cells option in creating a table is not available. |  | Done (Helped By Sharath | 2019-12-30 | Mergeing of rows and columns in table | Merge cells option is not available | No | Mergeing of cells option is required in creating tables. | Krishnam | Major |  | Done
ATAUTFRS22002 | Author | section assignment | Equation and symbols | Inserting special characters (≥,±,≤,®,.....) Option is not available. |  | Done (Kapish Jain) | 2019-12-30 | Inserting symbols (≥,±,≤,®,.....) and equations | Inserting symbol (≥,±,≤,®,.....) option is not available | No | Inserting symbol (≥,±,≤,®,.....) and equation option is required | Krishnam | Major
ATAUTFRS22003 | Author | section assignment | Company logo in title page | After updateing the documnet, the company logo is missing in the download file. |  | Tested again its working from Sharepoint or any URL | 2019-12-30 | Inserted company logo should be there in the download file | Logo is missing | No | Company logo is missing in the download file | Krishnam | Major
ATAUTFRS22004 | Author | section assignment | Session timeout | Session timeout message is not comeing until/unless we update the report. | Kapish/Sharath R&D | If any action performed by user after session time it will automatically Logged out. | 2019-12-30 | Session timeout message should popup after reaching the screen time out time | Session time out pop up message is not comeing | No | Session timeout message should popup after reaching the screen time out time but it was not showing untill we updateing the document. | Krishnam | Major
ATAUTFRS22005 | Author | section assignment | Table Wizard | Table wizard section tabs are not opening clearly. |  | Done (Kapish Jain) | 2019-12-30 | Table wizard section tabs Should opening clearly. | Table wizard section tabs are not opening clearly. | No | Sub tabs in table wizard section are not opening clearly. | Krishnam | Major
ATAUTFRS22006 | Author | section assignment | Inserting Tables | While copy paste tables, Boarders are missing. | Sharath/Nani | Partailly Done. Need more time for R&D | 2019-12-30 | Copy paste tables are required with out missing the boarders | Boarders are missing while copy paste the tables. | No | Copy paste tables are required with out missing the boarders | Krishnam | Major
ATAUTFRS22007 | Author | section assignment | Inserting Tables | Alignment ( Linespaceing) Option is not available. |  | Done (Kapish Jain) | 2019-12-30 | Alignment ( Linespaceing). | Alignment ( Linespaceing) Option is not available. | No | Line spaceing (alignment) option is required in Table wizard section. | Krishnam | Major
ATAUTFRS22008 | Author | section assignment | Text highlight color | Text highlight color button is not showing on my desktop |  | Worked | 2019-12-30 | Text highlight color button. | Text highlight color but is missing while useing the application | No | Text highlight color but is missing while useing the application | Krishnam | Major
ATAUTFRS22009 | Author | section assignment | Font size | Font size change is limited to 36pt. |  | Done (Kapish Jain) | 2019-12-30 | Font size change button is required beside the font change button. | Font size option is limited to 36pt. | No | Font size change options are not clear | Krishnam | Major
ATAUTFRS22010 | Author | section assignment | Application hanging (Not Frequently) | After inserting more pages of data while updateing the date the application is hanging. | Krishnam/Prasana | Have to test again | 2019-12-30 | Application should work while updateing the data | Application is hanging while updateing the data | No | Application is hanging while updateing the document. | Krishnam | Major
ATAUTFRS22011 | Author | section assignment | Font color | Changeing the text color is not available |  | Done (Kapish Jain) | 2019-12-30 | Change the color of text | Changeing the text color is not available | No | While inserting the data from word document, the text color is not changeing. | Krishnam | Major
ATAUTFRS22012 | Author | section assignment | Inserting image,Flow charts, Diagrams | Inserting data from local disk option is not available | Kapish/ Nani | Partailly Done. Need more time for R&D | 2019-12-30 | Inserting Images, flowcharts from local disk option is required. | There is no option to insert flowcharts, images from local disk. | No | Inserting images from local disk option is required. | Krishnam | Major
ATAUTFRS220123 | Author | section assignment | Font Change | While importing data from word document into AART, The font type and alignments are changeing | Sharath | Have to do R&D | 2019-12-30 | Font and alignments should not change | While importing data from word document into AART, The font type and alignments are changeing. | No | Font and alignments should not change | Krishnam | Major